## Burndown
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
39 | 10 | 30 | 0.33333
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-01-27 |  |  |  |  | 39 | 0 | 0 | 0 | 39 | 0
2020-02-10 | 30 |  | 10 | 30 | 39 | 0 | 10 | 0 | 29 | 0.33333
2020-02-24 | 30 |  |  |  | 29 | 10 | 10 | 30 | 19 | 0.33333
2020-03-09 | 30 |  | 6 | 40 | 19 | 10 | 16 | 30 | 13 | 0.22857
2020-03-23 | 30 | 8 | 4 | 30 | 21 | 16 | 20 | 70 | 17 | 0.2
2020-04-06 | 30 |  |  |  | 17 | 20 | 20 | 100 | 11 | 0.2
2020-04-20 | 30 | 2 | 2 | 18 | 13 | 20 | 22 | 100 | 11 | 0.18644
2020-05-04 | 30 | 34 | 11 | 18 | 45 | 22 | 33 | 118 | 34 | 0.24265
2020-05-18 | 30 | 3 | 6 | 24 | 37 | 33 | 39 | 136 | 31 | 0.24375
2020-06-01 | 0 |  |  |  | 31 | 39 | 39 | 160 | 31 | 0.24375
2020-06-15 | 0 |  |  |  | 31 | 39 | 39 | 160 | 31 | 0.24375
2020-06-29 | 30 | 13 | 2 | 30 | 44 | 39 | 41 | 160 | 42 | 0.21579
2020-07-13 | 0 |  |  |  | 42 | 41 | 41 | 190 | 42 | 0.21579
2020-07-27 | 0 |  |  |  | 42 | 41 | 41 | 190 | 42 | 0.21579
2020-08-10 | 0 |  |  |  | 42 | 41 | 41 | 190 | 42 | 0.21579
2020-08-24 | 0 |  |  |  | 42 | 41 | 41 | 190 | 42 | 0.21579
2020-09-07 | 0 |  |  |  | 42 | 41 | 41 | 190 | 42 | 0.21579
2020-09-21 | 36 |  | 0 | 30 | 42 | 41 | 41 | 190 | 42 | 0.18636
2020-10-05 | 36 | 2 | 2 | 36 | 44 | 41 | 43 | 220 | 42 | 0.16797
2020-10-19 | 36 | 3 | 3 | 36 | 45 | 43 | 46 | 256 | 42 | 0.15753
2020-11-02 | 36 |  | 3 | 36 | 42 | 46 | 49 | 292 | 39 | 0.14939
2020-11-16 | 36 | 5 | 2 | 36 | 44 | 49 | 51 | 328 | 42 | 0.14011
2020-11-30 | 36 |  | 0 | 36 | 42 | 51 | 51 | 364 | 42 | 0.1275
2020-12-14 | 27 | 3 | 8 | 27 | 45 | 51 | 59 | 400 | 37 | 0.13817
2020-12-28 | 0 |  | 0 | 0 | 37 | 59 | 59 | 427 | 37 | 0.13817
2021-01-11 | 36 |  | 8 | 36 | 37 | 59 | 67 | 427 | 29 | 0.14471
2021-01-25 | 36 |  | 5 | 36 | 29 | 67 | 72 | 463 | 24 | 0.14429
2021-02-08 | 18 |  | 4 | 18 | 24 | 72 | 76 | 499 | 20 | 0.147
2021-02-22 | 36 |  | 7 | 36 | 20 | 76 | 83 | 517 | 13 | 0.15009
2021-03-08 | 36 |  | 5 | 18 | 13 | 83 | 88 | 553 | 8 | 0.15412
2021-03-22 | 18 |  | 0 | 9 | 8 | 88 | 88 | 571 | 8 | 0.15172
2021-04-05 | 36 |  | 0 | 30 | 8 | 88 | 88 | 580 | 8 | 0.14426
2021-04-19 | 36 |  |  |  | 8 | 88 | 88 | 610 | 2.8066 | 0.14426
2021-05-03 | 36 |  |  |  | 2.8066 | 88 | 88 | 610 | 0 | 0.14426
2021-05-17 | 36 |  |  |  | 0 | 88 | 88 | 610 | 0 | 0.14426
2021-05-31 | 36 |  |  |  | 0 | 88 | 88 | 610 | 0 | 0.14426
2021-06-14 | 36 |  |  |  | 0 | 88 | 88 | 610 | 0 | 0.14426
2021-06-28 | 36 |  |  |  | 0 | 88 | 88 | 610 | 0 | 0.14426
| 513 |  | 4 | 19.1667
Formulas:
Open Story Points = [Open Story Points, row above]+14

## Backlog
Story ID | Story | Storypoints
1 | Wechseln auf neues DevKit | 1 | Done
2 | Verbesserung tracking impl. (Canvas) | 1 | Done |  | 11
3 | Implementation von Collision Detection | 2 | Done
4 | Tracking und Animation in 1 Projekt | 2 | Done
5 | Starten von Animation durch stehen auf homebutton | 1 | Done | Done if animation 1 start when a user stands on the Home button of the Smartphone
6 | Auswahl von Text durch User | 2 | Done | Done if User can chose one of four text Bubbles
7 | Animation Text auf smartphone | 2 | Done
8 | Smartphone fade out End of scene 1 | 1 | Done
9 | Text converten mit rotX | 2 | Done | Done if a Text can get convertet fia rotX
10 | Animation for encryption | 2 | Done | Done if the model and the animation of the enryption work
11 | Selection of rotX with tracking End of scene 2 | 3 | Done | Done when the User can choose a letter for the encryption
12 | Implement Game scene 3 | 13 SP sind aufgeteilt worden
13 | Create Animation of sending a message scene 4 | 8 | Done
14 | Create Animation message tower | 8 | Done
15 | Leaderboard scene 5 | 5 | Done
16 | Making Storys and Pm sheet | 2 | Done
17 | As a player i want to see scene nr1 in a retro style | 2 | Done | Done when the telefon is in a retro style and behaves properrly
18 | As a player i want to see a retro world in the background | 1 | Done | Done when the player sees a retro world in a dark theme with starts in the background
19 | fix burndown | 1 | Done
20 | Create Grid Floor | 2 | Done
21 | Make Storys for Scene3 | 1 | Done
22 | Fix Leaderboard Bugs | 1 | Done
23 | Scene3 - Create Canvas on the floor | 1 | Done
24 | Scene3 - Create different packet prefabs | 2 | Done
25 | Scene3 - Create 3 slot objects and slot absorbs packets it gets in touch with | 2 | Done
26 | Scene3 - Packet sticks to Person if the person gets in touch with packet | 2 | Done
27 | Scene3 - Create Packet Factory | 2 | Done
28 | Scene3 - Create object, that measures the time of the game | 3 | Done
29 | Scene3 - Save score to file | 2 | Done
30 | Adapt to double instance | 13
31 | Animation scene2 encryption | 3 | Done
32 | Scene 3 - Black hole | 2 | Done
33 | Create Scene 6 | 1 | Done
34 | Scene 6 - implement decryption | 3 | Done
35 | Scene 3 - new animation for moving letters | 3 | Done
36 | Scene 6 - new animation for decryption | 2 | Done
37 | Adapt to TUIO from TrackLink | 2 | Done
38 | Research double instancing | 5 | Done
39 | Adapt to double instance | 8

## Pmsheet
Task | Orig. Est | Curr. Est | Effort | Remain | Responsible
Story-16 | 2 | 2 | 0 | 2 | Kevin
Story-3 | 2 | 2 | 0 | 2 | Bochis
Story-9 | 2 | 2 | 0 | 2 | Anil
Story-16 | 2 | 2 | 2 | 0 | Kevin
Story-3 | 2 | 3 | 2 | 1 | Bochis
Story-9 | 2 | 1 | 2 | 0 | Anil
Story-10 | 2 | 2 | 0 | 2 | Anil
Story-7 | 2 | 2 | 0 | 2 | Kevin
Story-3 | 2 | 3 | 3 | 0 | Bochis
Story-10 | 2 | 3 | 2 | 1 | Anil
Story-7 | 2 | 2 | 2 | 0 | Kevin
Story18 | 1 | 1 | 1 | 0 | Kevin
Story-5 | 1 | 1 | 0 | 1 | Bochis
Story-10 | 2 | 4 | 3 | 1 | Anil
Story17 | 2 | 2 | 1 | 1 | Kevin
Story-5 | 1 | 1 | 0 | 1 | Bochis
Story-10 | 2 | 4 | 3 | 1 | Anil
Story17 | 2 | 2 | 1 | 1 | Kevin
Story 19 | 1 | 1 | 1 | 0 | Kevin
Story-6 | 3 | 3 | 3 | 0 | Bochis
Story-10 | 2 | 5 | 4 | 1 | Anil
Story-17 | 2 | 3 | 2 | 1 | Kevin
Story-20 | 2 | 2 | 0 | 2 | Kevin
2020-05-08
Story-17 | 2 | 3 | 3 | 0 | Kevin
Story-20 | 2 | 2 | 2 | 0 | Kevin
Story-12 | 13 | 14 | 1 | 13 | Bochis
Story-10 | 2 | 6 | 5 | 1 | Anil
2020-05-11
Story-22 | 1 | 1 | 1 | 0 | Anil
Story-21 | 1 | 1 | 1 | 0 | Bochis
Story-10 | 2 | 6 | 5 | 1 | Kevin
2020-05-15
Story-11 | 3 | 3 | 1 | 2 | Anil
Story-23 | 1 | 1 | 1 | 0 | Bochis
Story-10 | 2 | 7 | 6 | 1 | Kevin
2020-05-18
Story-11 | 3 | 3 | 3 | 0 | Anil
Story-24 | 2 | 2 | 2 | 0 | Bochis
Story-10 | 2 | 7 | 7 | 0 | Kevin
Date | Story-ID | Storypoints
2020-11-02 | 11 | 3
2020-11-16 | 29 | 2
2020-12-14 | 13 | 8
2021-01-11 | 14 | 8
2021-01-25 | 31 32 | 5
2021-02-08 | 33 34 | 4
2021-02-22 | 35 36 37 | 7