## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
47 | 0 | 1 | 0
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-02-10 | 36 |  | 10 | 30 | 47 | 0 | 10 | 0 | 37 | 0.33333
2020-02-24 | 36 |  | 2 | 36 | 37 | 10 | 12 | 30 | 35 | 0.18182
2020-03-09 | 36 |  |  |  | 35 | 12 | 12 | 66 | 28.4545 | 0.18182
2020-03-23 | 36 |  |  |  | 28.4545 | 12 | 12 | 66 | 21.9091 | 0.18182
2020-04-06 | 18 |  |  |  | 21.9091 | 12 | 12 | 66 | 18.6364 | 0.18182
2020-04-20 | 36 |  |  |  | 18.6364 | 12 | 12 | 66 | 12.0909 | 0.18182
2020-05-04 | 36 |  |  |  | 12.0909 | 12 | 12 | 66 | 5.5455 | 0.18182
2020-05-18 | 36 |  |  |  | 5.5455 | 12 | 12 | 66 | 0 | 0.18182
2020-06-01 | 36 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-06-15 | 36 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-06-29 | 36 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-07-13 | 0 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-07-27 | 0 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-08-10 | 0 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-08-24 | 36 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-09-07 | 36 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-09-21 | 36 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-10-05 | 36 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
2020-10-19 | 36 |  |  |  | 0 | 12 | 12 | 66 | 0 | 0.18182
| 0 |  | 15 | 20.8333
Formulas:
Open Story Points = [Open Story Points, row above]+14