## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
39 | 10 | 30 | 0.33333
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-01-27 | 30 |  |  |  | 39 | 0 | 0 | 0 | 39 | 0
2020-02-10 | 30 |  | 10 | 30 | 39 | 0 | 10 | 0 | 29 | 0.33333
2020-02-24 | 30 |  |  |  | 29 | 10 | 10 | 30 | 19 | 0.33333
2020-03-09 | 30 |  | 6 | 40 | 19 | 10 | 16 | 30 | 13 | 0.22857
2020-03-23 | 30 | 8 | 4 | 30 | 21 | 16 | 20 | 70 | 17 | 0.2
2020-04-06 | 30 |  |  |  | 17 | 20 | 20 | 100 | 11 | 0.2
2020-04-20 | 30 |  |  |  | 11 | 20 | 20 | 100 | 5 | 0.2
2020-05-04 | 30 |  |  |  | 5 | 20 | 20 | 100 | 0 | 0.2
2020-05-18 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-06-01 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-06-15 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-06-29 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-07-13 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-07-27 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-08-10 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-08-24 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-09-07 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-09-21 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
2020-10-05 | 30 |  |  |  | 0 | 20 | 20 | 100 | 0 | 0.2
| 230 |  | 4 | 19.1667
Formulas:
Open Story Points = [Open Story Points, row above]+14