## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
39 | 10 | 30 | 0.33333
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour) | Story ID | Story | Storypoints
2020-02-10 | 30 |  | 10 | 30 | 39 | 0 | 10 | 0 | 29 | 0.33333 | 1 | Wechseln auf neues DevKit | 1 | Done
2020-02-24 | 30 |  |  |  | 29 | 10 | 10 | 30 | 19 | 0.33333 | 2 | Verbesserung tracking impl. (Canvas) | 1 | Done
2020-03-09 | 30 |  |  |  | 19 | 10 | 10 | 30 | 9 | 0.33333 | 3 | Implementation von Collision Detection | 2
2020-03-23 | 30 |  |  |  | 9 | 10 | 10 | 30 | 0 | 0.33333 | 4 | Tracking und Animation in 1 Projekt | 2 | Done
2020-04-06 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 5 | Starten von Animation durch stehen auf homebutton | 1
2020-04-20 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 6 | Auswahl von Text durch User | 2
2020-05-04 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 7 | Animation Text auf smartphone | 2
2020-05-18 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 8 | Smartphone fade out End of scene 1 | 1 | Done
2020-06-01 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 9 | Text converten mit rotX | 1
2020-06-15 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 10 | Animation for encryption | 2
2020-06-29 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 11 | Selection of rotX with tracking End of scene 2 | 3
2020-07-13 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 12 | Implement Game scene 3 | 8
2020-07-27 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 13 | Create Animation of sending a message scene 4 | 8
2020-08-10 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 14 | Create Animation message tower | 8
2020-08-24 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 15 | Leaderboard scene 5 | 5 | Done
2020-09-07 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333 | 16 | Making Storys and Pm sheet | 2
2020-09-21 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333
2020-10-05 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333
2020-10-19 | 30 |  |  |  | 0 | 10 | 10 | 30 | 0 | 0.33333
| 0 |  | 15 | 20.8333
Formulas:
Open Story Points = [Open Story Points, row above]+14